## Construct
|  |  | remaining | initial
Construct 2 minigame |  |  | 0 | 14
DESIGNER : Zhai Guanxun
1. Minigame design document
User story : | As a trainer, I want to read a short document presenting a simple minigame that can be prototyped on Construct, so that I know what the trainee is planning to do, if he can explain it clearly, and make sure that the minigame fits the needs of the training.
Use Case |  |  |  | Status
The document presents the rules of the games |  |  |  | approved
The document presents the controls of the game |  |  |  | not approved
The document explain each mechanics that will be prototyped |  |  |  | not approved
The minigame is simple enough to be prototyped quickly with construct |  |  |  | approved
The document is short |  |  |  | not approved
The game intention is specific enough so that we can practice tuning the Minigame (casual / hardcore, slow /fast...) |  |  |  | approved
Tasks |  | progress | Work remaining | Initial work
Finish the game concept |  | completed | 0 | 0.5
Check whether the game is achievable with Construct 2 |  | completed | 0 | 1.5
Clearify the intention and write it down |  | completed | 0 | 0.25
Write down the rules & control & mechanics |  | completed | 0 | 1.5
Check the document and fix some problems |  | completed | 0 | 1
| Task3 | not done
|  | total | 0 | 4.75
2. Minigame First Playable
User story : | As a trainer, I want to play a basic prototype of the Minigame that was previously designed, featuring all mechanics working but without tuning, so that I can have a good idea of the game play and I can identify what elements we will have to tune to achieve the initial intention
Use Case |  |  |  | Status
The prototype is working without blocking bugs | The prototype is working without blocking bugs | The prototype is working without blocking bugs | The prototype is working without blocking bugs | not approved
The prototype has all its core features implemented | The prototype has all its core features implemented | The prototype has all its core features implemented | The prototype has all its core features implemented | not approved
The prototype is not tuned | The prototype is not tuned | The prototype is not tuned | The prototype is not tuned | not approved
A first list of parameters to tune later had been created | A first list of parameters to tune later had been generated | A first list of parameters to tune later had been generated | A first list of parameters to tune later had been generated | not approved
Tasks |  | progress | Work remaining | Initial work
Put all the sprites & background needed, and some animation |  | completed | 0 | 0.75
Write & arrange the event lines,Add counters & variables |  | completed | 0 | 2
Add congratulation scene |  | completed | 0 | 1
Check what elements are left then add them up |  | completed | 0 | 0.75
Test the first play | Task2 | completed | 0 | 0.5
List the parameters that needs tuning | Task3 | completed | 0 | 0.5
|  | total | 0 | 5.5
3. Minigame First pass tuning
User story : | As a trainer, I want the Minigame parameters to be tuned so that it fits its intention and can be playtested by others
Use Case |  |  |  | Status
The minigame plays and feel like its design intention | The minigame plays and feel like its design intention | The minigame plays and feel like its design intention | The minigame plays and feel like its design intention | not approved
The minigame is ready to be playtested | The minigame is ready to be playtested | The minigame is ready to be playtested | The minigame is ready to be playtested | not approved
Tasks |  | progress | Work remaining | Initial work
Check the parameters that can be tuned |  | not done
Check how the parameters affect the game |  | not done
Tune the parameter and suits it with the gameplay |  | not done
Test to adjust |  | not done
| Task2 | not done
| Task3 | not done
|  | total | 0 | 0
4. Minigame playtest
User story : | As a trainer, I want the minigame to be plastered, the feedbacks and their possible fixes listed so that we know how we can improve it
Use Case |  |  |  | Status
The minigame has been playtested at least once by another trainee | The minigame has been playtested at least once | The minigame has been playtested at least once | The minigame has been playtested at least once | not approved
The feedbacks are listed in a document | The feedbacks are listed in a document | The feedbacks are listed in a document | The feedbacks are listed in a document | not approved
Some possible solutions for each feedback are proposed | Some possible solutions for each feedback is proposed | Some possible solutions for each feedback is proposed | Some possible solutions for each feedback is proposed | not approved
Tasks |  | progress | Work remaining | Initial work
Ask 1st trainee to test and then fix the game according to the feedback |  | completed |  | 1
Ask 2nd trainee to test and then fix the game according to the feedback |  | not done |  | 1
Ask 2nd trainee to test and then fix the game according to the feedback(optional) |  | not done |  | 1
Summary the feedback and make the completed version |  | not done |  | 0.75
| Task2 | not done
| Task3 | not done
|  | total | 0 | 3.75
5. Minigame Final Interation
User story : | As a trainer, I want some of the feedbacks from the playtest to be addressed, so that the game is improved
Use Case |  |  |  | Status
UI is not friendly enough |  |  |  | not approved
Add more fun elements in the game |  |  |  | not approved
The feedback is not obvious |  |  |  | not approved
Tune the game to make it more leisure |  |  |  | not approved
Tasks |  | progress | Work remaining | Initial work
And the shining bar on the top |  | not done
Add the rule of prelong playing time(heart) |  | not done
Add animation to the heart and fix some events |  | not done
Add the rule of restore lightening |  | not done
| Task2 | not done
| Task3 | not done
|  | total | 0 | 0
Data : do not delete
not done
wip
completed
not approved
approved

## list
not started
wip
done